## Sheet1
Project Summary Costs
| Labor Total (Approximate) | 24602.9
| Furniture and Equipment | 74725
| Project Total (Approximate) | 99327.9
Labor Costs |  | Hourly Rate
| Project Manager | 65
| Isabella Smith | 55
| Art Peters | 50
| Bob DeSantis | 42.5
| Nick Thomas | 43.75
| Caroline Jansen | 45
| Average | 50.2083
Fiber Light
Initiating |  | Time (hrs) | Hourly Rate | Approx. Rate
| Develop project charter | 10 | 50.21 | 502.1
| Signing Contract | 2 | 50.21 | 100.42
| Meeting conference | 10 | 50.21 | 502.1
| Site Survey | 10 | 50.21 | 502.1
| Examine Requirements | 8 | 50.21 | 401.68
| Consider Potential Risks | 8 | 50.21 | 401.68
| Finalize Furniture supplier | 4 | 50.21 | 200.84
| Furniture Map Blueprint | 12 | 50.21 | 602.52
| Network Floor Plan | 8 | 50.21 | 401.68
Planning
| D&S Cubicle Furniture | 12 | 50.21 | 602.52
| D&S VoIP Phones | 8 | 50.21 | 401.68
| D&S Laptop computers | 8 | 50.21 | 401.68
| D&S Cat 6e cable | 8 | 50.21 | 401.68
| D&S Cisco wireless access points | 4 | 50.21 | 200.84
| D&S Kyocera color network printer-copier | 6 | 50.21 | 301.26
| D&S Ciena 3926 aggregation switch | 7 | 50.21 | 351.47
| Status Reporting 01 | 3 | 50.21 | 150.63
| Order Cubicle furniture | 8 | 50.21 | 401.68
| Order VoIP Phones | 6 | 50.21 | 301.26
| Order Laptop Computers | 8 | 50.21 | 401.68
| Order Cat 6e cable | 7 | 50.21 | 351.47
| Order Cisco wireless access point | 6 | 50.21 | 301.26
| Order Kyocera color network printer-copier | 5 | 50.21 | 251.05
| Order Ciena 3926 aggregation switch | 5 | 50.21 | 251.05
| Status Reporting 02 | 3 | 50.21 | 150.63
Executing
| R&I Cubicle Furniture | 29 | 50.21 | 1456.09
| R&I Voip Phones | 12 | 50.21 | 602.52
| R&I Laptop Computers | 12 | 50.21 | 602.52
| R&I Cat 6e cable | 10 | 50.21 | 502.1
| R&I Cisco wireless access points | 8 | 50.21 | 401.68
| R&I Kyocera color network printer | 4 | 50.21 | 200.84
| R&I Ciena 3926 aggregation switch | 6 | 50.21 | 301.26
| Status Reporting 03 | 3 | 50.21 | 150.63
| Install Cubicle Furniture | 36 | 50.21 | 1807.56
| Install VoIP phones | 12 | 50.21 | 602.52
| Install Laptop Computers | 18 | 50.21 | 903.78
| Install Cat 6e cable | 8 | 50.21 | 401.68
| Install Cisco wireless access points | 8 | 50.21 | 401.68
| Install Kyocera color network printer | 8 | 50.21 | 401.68
| Install Ciena 3926 aggregation switch | 6 | 50.21 | 301.26
| Status Reporting 04 | 3 | 50.21 | 150.63
| Inspect cubicle furniture | 10 | 50.21 | 502.1
| Test VoIP Phones | 4 | 50.21 | 200.84
| Test Laptop Computers | 7 | 50.21 | 351.47
| Test Cat 6e cable | 8 | 50.21 | 401.68
| Test Cisco wireless access points | 10 | 50.21 | 502.1
| Test Kyocera color network printer | 6 | 50.21 | 301.26
| Test Ciena 3926 aggregation switch | 6 | 50.21 | 301.26
| Status Reporting 05 | 3 | 50.21 | 150.63
Closing
| Review Status Reports | 6 | 50.21 | 301.26
| Intial Inspection | 12 | 50.21 | 602.52
| Fix open items | 11 | 50.21 | 552.31
| Check Softwares Authentication and Licensing | 3 | 50.21 | 150.63
| Gather all documents | 10 | 50.21 | 502.1
| Vendor Billing | 7 | 50.21 | 351.47
| Final Inspection and Sign-Off | 12 | 50.21 | 602.52
| Reported Problems | 4 | 50.21 | 200.84
| Proposed Solutions | 4 | 50.21 | 200.84
| Ideate Novel solutions | 5 | 50.21 | 251.05
| Release Project Team Members | 3 | 50.21 | 150.63
Total Work Hours
| Labor Total (Approximate) | 490 |  | 24602.9 | Total Work Hours * Average Labor Cost ($50.21)
|  |  |  | 24602.9 | Sum of all rate (approx.)
Furniture and Equipment Costs |  | Number | Cost | Total
| Laptops with software suite | 12 | 2125 | 25500
| VoIP Handsets | 12 | 545 | 6540
| Cubicle Furniture | 12 | 2600 | 31200
| Kyocera High-speed Copier/Printer | 1 | 5075 | 5075
| Cisco Aironet Wireless Access Points | 4 | 620 | 2480
| Ciena 3926 Aggregation Switch | 1 | 3450 | 3450
| Cat 6E Network Cabling | 1 | 480 | 480
| Furniture and Equipment Total |  |  | 74725